## ALL GOALS
Goal #1 - Establish Regional Leadership Approach (Regulation 679.510 a.1.i/v)
This section of the plan outlines the leadership structure through which Local Workforce Development Areas 3 and 4 will work to implement regional activities and outcomes over the first 2 years of the WIOA State Combined Plan. Included are specific strategies that ensure engage diverse constituencies are actively involved in decision-making.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible
1 | Define Regional Leadership | Complete | Initial roster submitted on time | Roster submitted with Regional Plan | Local Workforce Development Areas (LWDA) 3 and 4 - Boards & Staff
| 1a- Approach Formalized | Complete | Operational Agreement | Memorandum of Understanding (MOU) | LWDA 3 and 4 Workforce Boards & Staff
| 1b- Develop Job Description for Regional Leadership Team | 2017-05-01 | Documentation of scope, responsibilities, reporting mechanism, membership of committees, etc. | Job description approved by local Boards | Paula/Michelle with leadership team input and approval
| 1c- Describe constituencies represented by members of team | 2017-05-01 | Documentation of constituencies represented by members of the leadership team | Addendum to job description | Paula/Michelle
2 | Identify Strategies for Engaging Stakeholders | Feb-March 2017 | Specific strategies identified under Goals 5 and 7 | Minutes | Regional Leadership Team
3 | Implementation of Engagement Strategies (also reflected in Goal 7) | Varies by strategy (see below) | See below | See below | See below
| 3a - Duluth Workforce Development Board (DWDB) Diversity & Inclusion Task Force Established | Complete | Sub-group of DWDB to develop plan for how board can engage in relation to addressing employment disparities; Northeast Board to adopt effective strategies developed from the Duluth Board effort as well as outcomes from other planned events such as WFC focus groups and Marnita's Table. | Meeting Minutes, Meetings and/or Conversations with Community; Marnita's Table event | Staff and Task Force Members; AmeriCorps VISTA
| 3b - Marnita's Table Event | 2017-02-01 | Identify individuals and organizations to engage; understand how they want to be engaged; understand what those affected believe needs to change to address issues |  | Marnita's Table staff as contracted by DEED with assistance from Paula and Michelle as needed
| 3c - Outreach to learn how people of color and individuals in poverty feel about the Workforce Center (WFC); what is not welcoming and what can we do to change? | April-June 2017 | Development of strategies for making the WFC feel more welcoming to all people. | Outside facilitation of focus groups; partner with organizations such as Community Action Duluth, CHUM, SOAR, Take Action, AICHO, CJM committee, Indigenous Commission, and others; pulse surveys of those visiting WFC locations | Staff, VISTA Member, University of Minnesota Duluth (UMD) Center for Economic Development (CED) or hired consultant
| 3d - Engage with identified community leaders to provide input, make connections, engage in process, etc. | April-June 2017 | Identify individuals to engage in regional planning; implementation processes | Carl Crawford, City Human Rights Officer; Stephan Witherspoon, NAACP President; Jason Hollinday, Planning Director with the Fond du Lac Band of Lake Superior Chippewa; Larry Anderson, President, Fond du Lac Tribal and Community College | Staff and Board
| 3e - Participate in March 7th convening with Marnita's Table and representatives from each Region | 2017-03-17 | Awareness of outcomes from regional convenings; identification of key theme; initial identification of potential strategies for consideration | Notes from regional meetings and summary of March 7th notes | Staff
| 3f - Follow-up with key stakeholders identified at Marnita's Table event; Conduct outreach to (meet with) additional individuals and groups to expand base of information from Marnita's Table event | April-June 2017 | Discussion of highlights from Marnita's Table event; Increased understanding and awareness of populations experiencing inequities in education and employment; Discussion of engagement preferences | Documented notes or summary of discussions | Staff/Board
| 3g - Review of highlights from stakeholder meetings with Board | May-June 2017 | Board awareness of what community is saying and how to engage | Meeting Minutes | Staff/Board
| 3h - Development of engagement strategies and recruitment of key stakeholders | 2017-07-01 | Plan for engagement developed based on stakeholder feedback; key representatives identified | Documentation of engagement strategies; Roster | Staff/Board
| 3i - Structure/Plan in place for engaging identified populations in designing career pathways | By Fall 2017 | Career pathways reflect elements specific to identified populations | Minutes
| 3j - Investigate and pursue potential funding to support CP project to support identified populations | By June 2018 | Increased education and employment opportunities for identified populations | Funding Proposal; Award Letter; Work Plan
| 3k - Professional Development for Staff and Boards in areas specific to diversity, racism, cultural differences, bias, etc. | 2017-09-17 | Better understanding of implicit bias, micro aggressions, and cultural awareness | Participant evaluations | Workforce Development Board (WDB) Staff and WFC Partner Managers
4 | Regional Leadership Structure and Composition Established | 2017-05-16 | Commitment of representative WDB members to participate in Regional Leadership team | Team Roster/membership | WDB Members and Staff
| 4a - Key stakeholders representing affected populations are being engaged in planning efforts | Fall 2017 - ongoing | Stakeholders engaged in development of strategies; could include use of technology | Updated roster/structure | Staff, Board, Stakeholders
5 | Conduct Regional Asset Mapping Project | Oct-16 - June-17 | Comprehensive catalog of services and providers related to workforce development, including analysis of geographic and programmatic gaps and online GIS map of identified resources | Online and telephone surveys; final report and analysis compiled by UMD Bureau of Business and Economic Research (BBER) staff | UMD BBER under direction of the Regional Leadership Team and Board Staff
| 5a - Develop Request for Proposals (RFP) | Complete | Final RFP to select consultant for asset mapping initiative | Final RFP Document | Board Staff and Leadership Team
| 5b - Review Proposals and Select Consultant | Complete | Selection of single organization to conduct asset mapping | Documentation of Process - Minutes | Leadership Team
| 5c - Finalize contract, timeline and deliverables with Consultant | Complete | Approval of project timeline, schedule of ongoing check-in meetings, periodic updates to leadership team and boards | Signed Contract | UMD-BBER and Board Staff
| 5d - Conduct Mapping Process | October-16 thru June-17 | Finalized and implemented surveys; conduct follow up interviews; perform analysis and develop GIS maps | Documentation of Action Steps | UMD-BBER and Board Staff
| 5e - Mapping Process Complete | By June 1 2017 | Full catalog of workforce development-related assets for 7-county region; online mapping of resources searchable by type and geography; gap analysis report | Deliverables: Report and Online Tool | UMD-BBER
Goal #2 - Establish an Agreement for Negotiating local levels of Performance (Regulation 679.510 a.i.viii)
This section of the plan outlines the process by which Local Workforce Development Areas 3 and 4 will work to negotiate local levels of performance.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible
1 | Local boards identify who will participate in negotiations | 2017-01-01 | Roster of members | Meeting Minutes | Paula, Michelle, Carol Turner, Randy Back
2 | Develop a plan/process for negotiating local levels of performance | 2018-06-17 | Alignment with statewide expectation for a new negotiation process | Submission to State | Paula, Michelle, Carol Turner, Randy Back
| 2a - Local boards approve process for negotiating levels of performance | 2018-06-01 | Plan/Process for negotiating finalized | Meeting Minutes | Boards
| 2b - Initiate negotiations for local levels of performance | 2018-06-01 | Negotiations underway | Meeting Minutes | Paula, Michelle, Carol Turner, Randy Back
| 2c - Local levels of performance finalized | 2018-06-01 | Proposed levels finalized | Meeting Minutes | Paula, Michelle, Carol Turner, Randy Back
| 2d - Local levels of performance approved by local boards | 2018-06-01 | Boards approve | Meeting Minutes | Boards
Goal #3 - Identify and Implement 3 Regional Services (Career, Training and/or Support) Alignment Goals (Regulation 679.510 a.1.ii/vi)
This section of the plan identifies regional strategies for administration, career, training or support services that Local Workforce Development Areas 3 and 4 have identified and cooperatively commit to working on over the first 2 years of the WIOA State Combined Plan.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible
1 | Regional Leadership Identifies and Selects 3 Goals | Complete | Directives for Local area Directors/Staff | Minutes | Leadership Team, Boards & staff
| 1a - Coordinated Professional Development for Staff and Boards | 2017-09-01 | Cooperative Agreement Statement Developed and Approved; method for designing staff training established | Shared policy statements or service agreements | Partner Group
| 1b - Coordinated marketing and communication of WFC programs, events and initiatives | 2017-12-01 | Cooperative Agreement Statement Developed and Approved | Shared policy statements or service agreements | Partner Group; potential consultant or UMD CED project
| 1c - Coordinated Career Pathways Efforts; Joint working groups for Healthcare and Construction | Ongoing | Cooperative Agreement Statement Developed and Approved | Shared policy statements or service agreements | Leadership Team, Boards & staff
2 | Implementation of Identified Goals | Ongoing | Directives for Local area Directors/Staff | Minutes | Leadership Team, Boards & staff
| 2a - Professional Development Event for Staff and Boards | 2017-09-17 | Training conducted | Documentation of Agenda, List of participants | Partner Group
| 2b - Regional Marketing & Communications Plan Developed; Efforts Underway | by December 2017 | Coordinated marketing efforts in NE region | Plan document | Partner Group
| 2c - Active Working Group - Healthcare with specific initiatives underway | Ongoing | Strong, employer led sector partnerships with clearly defined pathways that facilitate access to employment | Minutes | Leadership Team, Boards & staff
| 2d - Active Working Group - Construction with specific initiatives underway | Ongoing | Strong, employer led sector partnerships with clearly defined pathways that facilitate access to employment | Minutes | Leadership Team, Boards & staff
3 | Regional Web Presence to including mapping data | by June 2017 | Web section on DWD and NEMOJT websites that highlight regional information including mapping results; regional strategies, etc. | Completed websites | Staff
Goal #4 - Coordination with Economic Development Services and Providers (Regulation 679.510 a.1.vii)
This section outlines strategies for aligning workforce development and economic development efforts with identified economic development partners across the region.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible
1 | Participation by board and/or staff in various economic development committees and organizations | Ongoing - Meeting schedules vary, but connectivity is at least monthly through one or more committees or groups | Increased awareness of economic development efforts and opportunities for collaboration; may include collaboration on a regional talent summit and/or assessment of skills present in the region | Listing of Economic Development (ED) groups, meeting dates and/or "link" - i.e. APEX, Arrowhead Growth Alliance (AGA), Duluth Mayor's Economic Development Committee, Duluth Economic Development Authority (DEDA), UMD Center for Economic Development, IRRRB, SBDC, EDAM | Board members & board staff
2 | Sharing of regional plan/priorities with economic development entities | 2017-12-01 | Increased awareness of workforce development resources, initiatives, and participation in meeting regional goals; validate that workforce goals support economic development goals | ED groups engaged in understanding regional workforce development goals, including IRRRB, APEX, Iron Range Economic Association (includes regional municipal EDAs), DEDA, Duluth Mayor's ED Committee, Chambers of Commerce, and the Arrowhead Growth Alliance | Board members & board staff
3 | Engage with Arrowhead Regional Development Commission's Comprehensive Economic Development Strategy regarding human capital and talent development | 2017-12-17 | Implement strategies related to workforce development outlined in latest CEDs report. | Evidence of addressing workforce development items from CEDS; may include new initiatives, refocusing current initiatives and programming, and/or aligning system resources with strategies outlined in CEDS | Board members & board staff
4 | Utilize ED networks to promote workforce system resources that help hire, train, and retain workers. | June 2018 | Increased use of On the Job Training, incumbent worker, internship and work experience resources | Increased number of participants in OJT, internship, work experience, and incumbent worker programs, including among participants of color and other disadvantaged populations | Board staff and WFC staff
5 | Better align locally with DEED Business & Community Development (BCD) staff | Ongoing | BCD staff have in-depth knowledge of WFC programs that assist with hiring, training and retaining workers and promote these programs and resources to business contacts | Increased utilization of WFC programs and resources by the business community | Board staff and BCD staff
6 | Assess board member connections | 2017-06-01 | Identify where board members are already engaged with economic development, professional organizations and other industry-specific entities so we can leverage those relationships for WFD efforts across the region | Conduct board member survey to capture affiliations and opportunities for networking leading to increased connectivity with ED organizations and professional associations; quarterly updates to local boards by members to keep apprised of what is happening in these groups | Board members and staff
| 6a - Develop and implement a systematic way for board members to report on happenings based on their involvement with ED groups and other professional associations; develop a template outlining what we'd like them to report | At Least Quarterly | Board is informed of economic development activities and opportunities for coordination | Meeting minutes reflect updates | Board and staff
Goal #5 - Identify the Populations Experiencing Inequities in Educational and Employment Outcomes (State Plan Goal #1)
This section outlines the basis for identifying populations most affected by educational/employment disparities and gaps in services for identified populations.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible
1 | Assess demographic data | March 2017 | Understand who is impacted | LMI Data report | Board & staff
2 | Utilize asset mapping initiative to identify gaps in services for identified populations | June 2017 | Understanding of populations that lack services geographically or programmatically | Asset Mapping final report | Board and board staff
3 | Identify community leaders and organizations that serve disadvantaged populations such as food banks, goodwill, Salvation Army, Ruby's Pantry, etc., to engage in strategies outlined in Goal 7 | 2017-06-17 | Know who is serving populations experiencing inequities and with whom to connect; establish network of providers through which we can engage stakeholders, conduct focus groups, and conduct program outreach to ensure greater awareness of system resources | List of organizations and leaders identified through board and staff networks; asset mapping initiative, Marnita's Table event, and others | Board, Leadership Team & Staff
4 | Marnita's Table event | 2017-02-01 | Increased understanding and awareness of populations experiencing inequities in education and employment | Report from Marnita's Table | Board, Staff, Marnita's Table
Goal #6 - Create 1-3 Business Led Sector Partnerships (Regulation 679.510 a.1.iii/iv/vii and State Plan - Strategic Element #1)
This section outlines the industry sectors identified for career pathways and employer-led partnerships in Region 2, including the expected outcomes to be achieved over the two-year program period for this goal.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible
1 | Assess LMI to identify key sectors with demand occupations | Dec-15 | Understand which sectors are key to the regional economy | DEED LMI - Regional Overview prepared by Erik White | Board and staff
2 | HEALTHCARE: Employer led sector partnership established | 2015-12-01 | Businesses and partners engaged in supporting employer led sector partnership efforts in Healthcare | Roster of sector partnership members | Duluth WDB, Board staff, Rural Coordinator
| 2a - Map pathways for demand occupations | By January 2017 | Pathways documented | Final documents | Working Group and Staff
| 2b - Raise awareness of occupations in demand and pathways | Spring 2017(Duluth) | Increased awareness of how to access and move forward within the healthcare industry | Awareness Events Documented | Working Group and Staff
| 2c - Implement strategies for moving people into pathways - i.e. P2P grant | Ongoing | Participants complete training and enter healthcare occupations | # trained, # hired | Working Group, Staff, Partners, Boards
| 2d - Work with Maher and Maher to develop strategies for expanding working group and identify employer leaders and plan for sustainability of effective initiatives | May - June 2017 | Strategies developed and recruitment begins | Work with Maher & Maher documented | Staff, Employers, Key Stakeholders
| 2f - Expanded working group established | By Fall 2017 | Broadly representative, employer-led partnership established | Roster | Staff, Employers, Key Stakeholders
| 2h- Facilitate discussion and planning for regional sector strategy development | Winter-Spring 2018 | Establish buy-in for regional sector partnership and identified strategies | Minutes | Staff, Employers, Key Stakeholders
| 2i - Initiate implementation of identified sector strategy/ies | By June 2018 | Sector strategies being implemented | Minutes | Staff, Employers, Key Stakeholders
| 2g- Sustainability plan developed; implementation begins | By June 2018 | Sources of support for effective initiatives identified | Sustainability Plan | Staff, Employers, Key Stakeholders
3 | CONSTRUCTION/SKILLED TRADES: Employer led sector partnership established | 2018-06-01 | Employers, unions, contractors and partners engaged in supporting employer led sector partnership efforts in Construction/Skilled Trades | Roster of sector partnership members | Skilled Trades committee of the Northeast WDB with representation of Duluth WDB; Rural Coordinator
| 3a - Work with Maher and Maher to develop strategies for expand working group and identify employer leaders | May - June 2017 | Strategies developed and recruitment begins | Work with Maher & Maher documented | Staff, Employers, Key Stakeholders
| 3b - Map pathways for demand occupations | By June 2017 | Entry into and advancement within key skilled trades, including apprenticeships and post secondary program opportunities | Documents reflecting career pathways of key trades | Skilled Trades committee of the Northeast WDB with representation of Duluth WDB; Rural Coordinator
| 3c - Raise awareness of occupations in demand and pathways | Fall 2017 | Communication initiative to educate students, teachers, parents, career counselors and the public at large about opportunities within the skilled trades | Developed materials illustrating career pathway opportunities in skilled trades | Skilled Trades committee of the Northeast WDB with representation of Duluth WDB; Rural Coordinator
| 3d- Expand working group to include additional employers, trades representatives, and key stakeholders; identify leaders | Fall 2017 | Broadly representative, employer-led partnership established | Roster | Staff, Employers, Key Stakeholders
| 3e- Facilitate discussion and planning for regional sector strategy development | Winter-Spring 2018 | Establish buy-in for regional sector partnership and identified strategies | Minutes | Staff, Employers, Key Stakeholders
| 3f - Initiate implementation of identified sector strategy/ies | Spring 2018 | Sector strategies being implemented | Minutes | Staff, Employers, Key Stakeholders
| 3g - Implement strategies for moving people into pathways | By June 2018 | Possible cohort training to move people into skilled trades; may include instruction in basic applied construction skills or P2P-like projects; facilitate connections between skilled trades reps and local high schools | Number of methods used to promote skilled trades opportunities | Skilled Trades committee of the Northeast WDB with representation of Duluth WDB; Rural Coordinator
4 | Training and Education Partners Identified and Engaged | Jun-18 | Training providers see the value in developing non-traditional ways of delivering training and understand their role(s) | Faculty at local colleges engaged in program design and implementation | Career Pathways committees, boards, and staff
| 4a - Identify key contacts at local training and education facilities | By Jun-18 | Individuals and contact information is compiled | Contact list | Staff, Boards and Committees
| 4b - Connections with key contacts made; either individually or group (1 or more meetings) | By Jun-18 | Introductions are made; Basic education about WF system/education and training partners; career pathways; discussion of changing education and training needs | Minutes; Plan for moving forward | Staff, Boards and Committees
| 4c - WF system partners and training & education partners engaged and working together | By Jun-18 | Education and Training Partners engaged with WF System partners (Committee Roster, Minutes) | Committee Roster, Minutes | Staff, Boards and Committees
5 | Support Partners Identified and Engaged | Jun-18 | Existing and new partners identified through asset mapping process engaged in program design and understand their role(s) | Number of participating organizations | Career Pathways committees, boards, and staff
| 5a - Review final report from consultant | Summer 2017 | Initial understanding of assessment findings | Final Report
| 5b - Establish working group to develop recommendations for action | Fall 2017 | Group to thoroughly evaluate report to identify needed action | Roster of members; Minutes
| 5c - Formalize recommended actions | Spring 2018 | Clear recommendations for action based on mapping results | Minutes
| 5d - Implement recommended actions | Summer 2018 | Clear plan for moving forward | Minutes; Board Action
6 | Converse with Maher and Maher to learn about available resources and support | May-June 2017 | Awareness of technical assistance resources | Notes; Listing | Staff
| 6a - Review available resources with Board; Select appropriate direction | May-June 2017 | Board identification of technical assistance needs; plan for next steps | Minutes | Staff, Boards
| 6b - Implement technical assistance services | June-August 2017 | Technical Assistance services provided by Maher and Maher | Documentation of activities | Staff, Boards, Key Stakeholders
Goal #7 - Stakeholder Engagement (State Plan - Strategic Element #2)
This section outlines how the Workforce Development Boards in Region 2 will engage stakeholders, particularly populations experiencing the greatest inequities in educational and employment outcomes, in the development and implementation of local and regional strategies.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible
1 | Meet/engage with identified representatives | 2017-06-01 | Understand best way to engage and learn what affected populations believe needs to happen so change can occur | Roster of population representatives; notes from conversations/meetings | Board, Leadership Team & Staff
| 1a - Host stakeholder event in partnership with Marnita's Table | 2017-02-01 | Relationship development; new connections; increased understanding of issues/challenges; ideas for moving forward | Participation list; report from Marnita's Table | Board, Staff
1b - Please reference additional actions outlined in Goal 1
| 1b- Conduct series of shared professional development trainings for staff of all WFC partners in the areas of implicit bias, micro aggressions, cultural awareness, and hiring practices. | 2017-09-17 | All program staff, supervisors and management have a greater awareness of cultural differences and similarities, communication styles and preferences, as well as a renewed understanding of how their own biases and world views can impact working relationships. | Pre- post-training/workshop evaluations | WFC Partner Management
2 | Develop system-wide coordinated strategies to engage more individuals with disabilities in employment activities | June 2018 | increased number of enrolled program/initiative participants reporting a disability; | Documentation of established processes to increase participation of individuals with disabilities in system programs and initiatives. | Board, WFC Partner Management
| 2a - Identify how WFC system can assist with preparing residential care staff to assess residents' employment potential | June 2017 | Gain understanding of changing regulations that affect community-based employment requirements of local residential/adult care facilities | A facilitated meeting with residential care and sheltered workshop facilities to determine how the workforce development system can assist with assessing residents' work skills and community-based employment potential | WFC partner management, including VRS
| 2b - Provide career planning and exploration resources to youth with disabilities | Ongoing | more youth with disabilities have post-secondary employment and/or training plans | Activity tracking akin to current Career EdVenture tracking methodology | youth program staff, including VRS transitions staff
3 | Use networks established in goal #5 to engage people in poverty and other identified target populations | through June 2018 | Opportunity to connect with non-program participants on employment needs and barriers to accessing system resources | Number of non-profit community services used for outreach; number of individual WFC-oriented focus groups conducted | Board and program staff
| 3a - Identify consultant to facilitate focus groups to discern what will enhance welcoming atmosphere and outreach opportunities of local WFCs | Sept-17 | Recommendations to improve how WFCs interact with identified populations |  | Board staff
| 3b - Develop focus group questions with consultant | Sept-17 | comprehensive strategy to identify local system improvements | Outcomes of focus groups | Board staff/WFC partner management
4 | Increase collaboration with Native American populations | 2017-12-01 | More frequent collaboration with Tribal employment and training programs and increased number of Native Americans program participants | increase of number of Native American participants in programs and initiatives; Native American participation on regional leadership/boards | Boards, board staff, program administration and staff
| 4a - Maintain presence at Fond du Lac Tribal and Community College | Ongoing | Increased participation of Native Americans in programs & initiatives; | Consistent and regular presence of counseling staff at FDLTCC | NEMOJT staff
| 4b - Connect with tribal WIOA programs to identify opportunities for alignment and leveraging funds to achieve shared goals | 2017-06-01 | Understanding of Tribal WIOA programs and identified opportunities for working closer | Identification and engagement of tribal WIOA program contacts | NEMOJT administration
| 4c - Educate staff on Native American culture | September-17 | Staff gain better understanding of factors affecting Native American education, employment, and cultural aspects that influence Native individuals; counseling staff become more culturally sensitive and creative when designing employment and training strategies for Native participants; counseling staff become aware of any implicit bias or micro aggressions that may negatively impact their interactions with Native participants | Number of training sessions; workshop evaluations; all partner staff receive training | WFC partner management
5 | Connect with groups that are already working on these issues - Take Action, Employment Table, Cross Cultural Alliance, state agencies, etc. | Ongoing | Increased collaboration and information sharing around key issues; reduced duplication of efforts | Report outs in Board Minutes and documentation of meetings | Board and staff
Goal #8 - Submission of Local Plans that Align with the Regional Plan (Regulation 679.510.2.ii)
This section documents action related to review and approval of Local and Regional Plans (Local Areas 3 and 4; Region 2) over the first 2 years of the WIOA State Combined Plan.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible
1 | LWDA 3 Submission of Local Plan | Plan submitted | Review and Approval of Local Plan by DEED | Confirmation from DEED (pending) | Michelle Ufford
2 | LWDA 4 Submission of Local Plan | Plan submitted | Review and Approval of Local Plan by DEED | Confirmation from DEED (pending) | Paula Reed
3 | Submission of Regional Plan for Region 2 | 2017-03-01 | Review and Approval of Regional Plan by DEED | Confirmation from DEED | Michelle Ufford and Paula Reed

## GOAL #1
Goal #1 - Establish Regional Leadership Approach (Regulation 679.510 a.1.i/v)
This section of the plan outlines the leadership structure through which Local Workforce Development Areas 3 and 4 will work to implement regional activities and outcomes over the first 2 years of the WIOA State Combined Plan. Included are specific strategies that ensure engage diverse constituencies are actively involved in decision-making.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Define Regional Leadership | Complete | Initial roster submitted on time | Roster submitted with Regional Plan | Local Workforce Development Areas (LWDA) 3 and 4 - Boards & Staff
| 1a- Approach Formalized | Complete | Operational Agreement | Memorandum of Understanding (MOU) | LWDA 3 and 4 Workforce Boards & Staff
| 1b- Develop Job Description for Regional Leadership Team | 2017-03-01 | Documentation of scope, responsibilities, reporting mechanism, membership of committees, etc. | Job description approved by local Boards | Paula/Michelle with leadership team input and approval | With review by leadership group and approval by boards
| 1c- Describe constituencies represented by members of team | 2017-03-01 | Documentation of constituencies represented by members of the leadership team | Addendum to job description | Paula/Michelle
2 | Identify Strategies for Engaging Stakeholders | Feb-March 2017 | Specific strategies identified under Goals 5 and 7 | Minutes | Regional Leadership Team
3 | Implementation of Engagement Strategies (also reflected in Goal 7) | Varies by strategy (see below) | See below | See below | See below
| 3a - Duluth Workforce Development Board (DWDB) Diversity & Inclusion Task Force Established | Complete | Sub-group of DWDB to develop plan for how board can engage in relation to addressing employment disparities; Northeast Board to adopt effective strategies developed from the Duluth Board effort as well as outcomes from other planned events such as WFC focus groups and Marnita's Table. | Meeting Minutes, Meetings and/or Conversations with Community; Marnita's Table event | Staff and Task Force Members; AmeriCorps VISTA
| 3b - Marnita's Table Event | 2017-02-01 | Identify individuals and organizations to engage; understand how they want to be engaged; understand what those affected believe needs to change to address issues |  | Marnita's Table staff as contracted by DEED with assistance from Paula and Michelle as needed
| 3c - Outreach to learn how people of color and individuals in poverty feel about the Workforce Center (WFC); what is not welcoming and what can we do to change? | April-June 2017 | Development of strategies for making the WFC feel more welcoming to all people. | Outside facilitation of focus groups; partner with organizations such as Community Action Duluth, CHUM, SOAR, Take Action, AICHO, CJM committee, Indigenous Commission, and others; pulse surveys of those visiting WFC locations | Staff, VISTA Member, University of Minnesota Duluth (UMD) Center for Economic Development (CED) or hired consultant
| 3d - Engage with identified community leaders to provide input, make connections, engage in process, etc. | April-June 2017 | Identify individuals to engage in regional planning; implementation processes | Carl Crawford, City Human Rights Officer; Stephan Witherspoon, NAACP President; Jason Hollinday, Planning Director with the Fond du Lac Band of Lake Superior Chippewa; Larry Anderson, President, Fond du Lac Tribal and Community College | Staff and Board
| 3e - Participate in March 7th convening with Marnita's Table and representatives from each Region | 2017-03-17 | Awareness of outcomes from regional convenings; identification of key theme; initial identification of potential strategies for consideration | Notes from regional meetings and summary of March 7th notes | Staff
| 3f - Follow-up with key stakeholders identified at Marnita's Table event; Conduct outreach to (meet with) additional individuals and groups to expand base of information from Marnita's Table event | April-June 2017 | Discussion of highlights from Marnita's Table event; Increased understanding and awareness of populations experiencing inequities in education and employment; Discussion of engagement preferences | Documented notes or summary of discussions | Staff/Board
| 3g - Review of highlights from stakeholder meetings with Board | May-June 2017 | Board awareness of what community is saying and how to engage | Meeting Minutes | Staff/Board
| 3h - Development of engagement strategies and recruitment of key stakeholders | 2017-07-01 | Plan for engagement developed based on stakeholder feedback; key representatives identified | Documentation of engagement strategies; Roster | Staff/Board
| 3i - Structure/Plan in place for engaging identified populations in designing career pathways | By Fall 2017 | Career pathways reflect elements specific to identified populations | Minutes
| 3j - Investigate and pursue potential funding to support CP project to support identified populations | By June 2018 | Increased education and employment opportunities for identified populations | Funding Proposal; Award Letter; Work Plan
| 3k - Professional Development for Staff and Boards in areas specific to diversity, racism, cultural differences, bias, etc. | 2017-09-17 | Better understanding of implicit bias, micro aggressions, and cultural awareness | Participant evaluations | Workforce Development Board (WDB) Staff and WFC Partner Managers
4 | Regional Leadership Structure and Composition Established | 2017-05-16 | Commitment of representative WDB members to participate in Regional Leadership team | Team Roster/membership | WDB Members and Staff
| 4a - Key stakeholders representing affected populations are being engaged in planning efforts | Fall 2017 - ongoing | Stakeholders engaged in development of strategies; could include use of technology | Updated roster/structure | Staff, Board, Stakeholders
5 | Conduct Regional Asset Mapping Project | Oct-16 - June-17 | Comprehensive catalog of services and providers related to workforce development, including analysis of geographic and programmatic gaps and online GIS map of identified resources | Online and telephone surveys; final report and analysis compiled by UMD Bureau of Business and Economic Research (BBER) staff | UMD BBER under direction of the Regional Leadership Team and Board Staff
| 5a - Develop Request for Proposals (RFP) | Complete | Final RFP to select consultant for asset mapping initiative | Final RFP Document | Board Staff and Leadership Team
| 5b - Review Proposals and Select Consultant | Complete | Selection of single organization to conduct asset mapping | Documentation of Process - Minutes | Leadership Team
| 5c - Finalize contract, timeline and deliverables with Consultant | Complete | Approval of project timeline, schedule of ongoing check-in meetings, periodic updates to leadership team and boards | Signed Contract | UMD-BBER and Board Staff
| 5d - Conduct Mapping Process | October-16 thru June-17 | Finalized and implemented surveys; conduct follow up interviews; perform analysis and develop GIS maps | Documentation of Action Steps | UMD-BBER and Board Staff
| 5e - Mapping Process Complete | By June 1 2017 | Full catalog of workforce development-related assets for 7-county region; online mapping of resources searchable by type and geography; gap analysis report | Deliverables: Report and Online Tool | UMD-BBER

## GOAL #2
Goal #2 - Establish an Agreement for Negotiating local levels of Performance (Regulation 679.510 a.i.viii)
This section of the plan outlines the process by which Local Workforce Development Areas 3 and 4 will work to negotiate local levels of performance.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Local boards identify who will participate in negotiations | 2017-01-01 | Roster of members | Meeting Minutes | Paula, Michelle, Carol Turner, Randy Back
2 | Develop a plan/process for negotiating local levels of performance | 2018-06-17 | Alignment with statewide expectation for a new negotiation process | Submission to State | Paula, Michelle, Carol Turner, Randy Back
| 2a - Local boards approve process for negotiating levels of performance | 2018-06-01 | Plan/Process for negotiating finalized | Meeting Minutes | Boards
| 2b - Initiate negotiations for local levels of performance | 2018-06-01 | Negotiations underway | Meeting Minutes | Paula, Michelle, Carol Turner, Randy Back
| 2c - Local levels of performance finalized | 2018-06-01 | Proposed levels finalized | Meeting Minutes | Paula, Michelle, Carol Turner, Randy Back
| 2d - Local levels of performance approved by local boards | 2018-06-01 | Boards approve | Meeting Minutes | Boards

## GOAL #3
Goal #3 - Identify and Implement 3 Regional Services (Career, Training and/or Support) Alignment Goals (Regulation 679.510 a.1.ii/vi)
This section of the plan identifies regional strategies for administration, career, training or support services that Local Workforce Development Areas 3 and 4 have identified and cooperatively commit to working on over the first 2 years of the WIOA State Combined Plan.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Regional Leadership Identifies and Selects 3 Goals | Complete | Directives for Local area Directors/Staff | Minutes | Leadership Team, Boards & staff
| 1a - Coordinated Professional Development for Staff and Boards | 2017-09-01 | Cooperative Agreement Statement Developed and Approved; method for designing staff training established | Shared policy statements or service agreements | Partner Group
| 1b - Coordinated marketing and communication of WFC programs, events and initiatives | 2017-12-01 | Cooperative Agreement Statement Developed and Approved | Shared policy statements or service agreements | Partner Group; potential consultant or UMD CED project
| 1c - Coordinated Career Pathways Efforts; Joint working groups for Healthcare and Construction | Ongoing | Cooperative Agreement Statement Developed and Approved | Shared policy statements or service agreements | Leadership Team, Boards & staff
2 | Implementation of Identified Goals | Ongoing | Directives for Local area Directors/Staff | Minutes | Leadership Team, Boards & staff
| 2a - Professional Development Event for Staff and Boards | 2017-09-17 | Training conducted | Documentation of Agenda, List of participants | Partner Group
| 2b - Regional Marketing & Communications Plan Developed; Efforts Underway | by December 2017 | Coordinated marketing efforts in NE region | Plan document | Partner Group
| 2c - Active Working Group - Healthcare with specific initiatives underway | Ongoing | Strong, employer led sector partnerships with clearly defined pathways that facilitate access to employment | Minutes | Leadership Team, Boards & staff
| 2d - Active Working Group - Construction with specific initiatives underway | Ongoing | Strong, employer led sector partnerships with clearly defined pathways that facilitate access to employment | Minutes | Leadership Team, Boards & staff
3 | Regional Web Presence to include mapping data | by June 2017 | Web section on DWD and NEMOJT websites that highlight regional information including mapping results; regional strategies, etc. | Completed websites | Staff

## GOAL #4
Goal #4 - Coordination with Economic Development Services and Providers (Regulation 679.510 a.1.vii)
This section outlines strategies for aligning workforce development and economic development efforts with identified economic development partners across the region.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Participation by board and/or staff in various economic development committees and organizations | Ongoing - Meeting schedules vary, but connectivity is at least monthly through one or more committees or groups | Increased awareness of economic development efforts and opportunities for collaboration; may include collaboration on a regional talent summit and/or assessment of skills present in the region | Listing of Economic Development (ED) groups, meeting dates and/or "link" - i.e. APEX, Arrowhead Growth Alliance (AGA), Duluth Mayor's Economic Development Committee, Duluth Economic Development Authority (DEDA), UMD Center for Economic Development, IRRRB, SBDC, EDAM | Board members & board staff | The Arrowhead Growth Alliance includes representatives from most of the entities listed and these meetings occur quarterly. While additional connections are made between these meetings, we are assured of a meaningful connection at least quarterly.
2 | Sharing of regional plan/priorities with economic development entities | 2017-12-01 | Increased awareness of workforce development resources, initiatives, and participation in meeting regional goals; validate that workforce goals support economic development goals | ED groups engaged in understanding regional workforce development goals, including IRRRB, APEX, Iron Range Economic Association (includes regional municipal EDAs), DEDA, Duluth Mayor's ED Committee, Chambers of Commerce, and the Arrowhead Growth Alliance | Board members & board staff
3 | Engage with Arrowhead Regional Development Commission's Comprehensive Economic Development Strategy regarding human capital and talent development | 2017-12-17 | Implement strategies related to workforce development outlined in latest CEDs report. | Evidence of addressing workforce development items from CEDS; may include new initiatives, refocusing current initiatives and programming, and/or aligning system resources with strategies outlined in CEDS | Board members & board staff
4 | Utilize ED networks to promote workforce system resources that help hire, train, and retain workers. | June 2018 | Increased use of On the Job Training, incumbent worker, internship and work experience resources | Increased number of participants in OJT, internship, work experience, and incumbent worker programs, including among participants of color and other disadvantaged populations | Board staff and WFC staff
5 | Better align locally with DEED Business & Community Development (BCD) staff | Ongoing | BCD staff have in-depth knowledge of WFC programs that assist with hiring, training and retaining workers and promote these programs and resources to business contacts | Increased utilization of WFC programs and resources by the business community | Board staff and BCD staff
6 | Assess board member connections | 2017-06-01 | Identify where board members are already engaged with economic development, professional organizations and other industry-specific entities so we can leverage those relationships for WFD efforts across the region | Conduct board member survey to capture affiliations and opportunities for networking leading to increased connectivity with ED organizations and professional associations; quarterly updates to local boards by members to keep apprised of what is happening in these groups | Board members and staff
| 6a - Develop and implement a systematic way for board members to report on happenings based on their involvement with ED groups and other professional associations; develop a template outlining what we'd like them to report | At Least Quarterly | Board is informed of economic development activities and opportunities for coordination | Meeting minutes reflect updates | Board and staff | The Northeast WDB allocates time on every agenda for members to report on happenings and issues in their sector/organization; this often includes economic development efforts and partnerships.

## GOAL #5
Goal #5 - Identify the Populations Experiencing Inequities in Educational and Employment Outcomes (State Plan Goal #1)
This section outlines the basis for identifying populations most affected by educational/employment disparities and gaps in services for identified populations.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Assess demographic data | March 2017 | Understand who is impacted | LMI Data report | Board & staff
2 | Utilize asset mapping initiative to identify gaps in services for identified populations | June 2017 | Understanding of populations that lack services geographically or programmatically | Asset Mapping final report | Board and board staff
3 | Identify community leaders and organizations that serve disadvantaged populations such as food banks, goodwill, Salvation Army, Ruby's Pantry, etc., to engage in strategies outlined in Goal 7 | 2017-06-17 | Know who is serving populations experiencing inequities and with whom to connect; establish network of providers through which we can engage stakeholders, conduct focus groups, and conduct program outreach to ensure greater awareness of system resources | List of organizations and leaders identified through board and staff networks; asset mapping initiative, Marnita's Table event, and others | Board, Leadership Team & Staff
4 | Marnita's Table event | 2017-02-01 | Increased understanding and awareness of populations experiencing inequities in education and employment | Report from Marnita's Table | Board, Staff, Marnita's Table

## GOAL #6
Goal #6 - Create 1-3 Business Led Sector Partnerships (Regulation 679.510 a.1.iii/iv/vii and State Plan - Strategic Element #1)
This section outlines the industry sectors identified for career pathways and employer-led partnerships in Region 2, including the expected outcomes to be achieved over the two-year program period for this goal.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Assess LMI to identify key sectors with demand occupations | Dec-15 | Understand which sectors are key to the regional economy | DEED LMI - Regional Overview prepared by Erik White | Board and staff
2 | HEALTHCARE: Employer led sector partnership established | 2015-12-01 | Businesses and partners engaged in supporting employer led sector partnership efforts in Healthcare | Roster of sector partnership members | Duluth WDB, Board staff, Rural Coordinator
| 2a - Map pathways for demand occupations | By January 2017 | Pathways documented | Final documents | Working Group and Staff
| 2b - Raise awareness of occupations in demand and pathways | Spring 2017(Duluth) | Increased awareness of how to access and move forward within the healthcare industry | Awareness Events Documented | Working Group and Staff
| 2c - Implement strategies for moving people into pathways - i.e. P2P grant | Ongoing | Participants complete training and enter healthcare occupations | # trained, # hired | Working Group, Staff, Partners, Boards
| 2d - Work with Maher and Maher to develop strategies for expanding working group and identify employer leaders and plan for sustainability of effective initiatives | May - June 2017 | Strategies developed and recruitment begins | Work with Maher & Maher documented | Staff, Employers, Key Stakeholders
| 2f - Expanded working group established | By Fall 2017 | Broadly representative, employer-led partnership established | Roster | Staff, Employers, Key Stakeholders
| 2h- Facilitate discussion and planning for regional sector strategy development | Winter-Spring 2018 | Establish buy-in for regional sector partnership and identified strategies | Minutes | Staff, Employers, Key Stakeholders
| 2i - Initiate implementation of identified sector strategy/ies | By June 2018 | Sector strategies being implemented | Minutes | Staff, Employers, Key Stakeholders
| 2g- Sustainability plan developed; implementation begins | By June 2018 | Sources of support for effective initiatives identified | Sustainability Plan | Staff, Employers, Key Stakeholders
3 | CONSTRUCTION/SKILLED TRADES: Employer led sector partnership established | 2018-06-01 | Employers, unions, contractors and partners engaged in supporting employer led sector partnership efforts in Construction/Skilled Trades | Roster of sector partnership members | Skilled Trades committee of the Northeast WDB with representation of Duluth WDB; Rural Coordinator
| 3a - Work with Maher and Maher to develop strategies for expand working group and identify employer leaders | May - June 2017 | Strategies developed and recruitment begins | Work with Maher & Maher documented | Staff, Employers, Key Stakeholders
| 3b - Map pathways for demand occupations | By June 2017 | Entry into and advancement within key skilled trades, including apprenticeships and post secondary program opportunities | Documents reflecting career pathways of key trades | Skilled Trades committee of the Northeast WDB with representation of Duluth WDB; Rural Coordinator
| 3c - Raise awareness of occupations in demand and pathways | Fall 2017 | Communication initiative to educate students, teachers, parents, career counselors and the public at large about opportunities within the skilled trades | Developed materials illustrating career pathway opportunities in skilled trades | Skilled Trades committee of the Northeast WDB with representation of Duluth WDB; Rural Coordinator
| 3d- Expand working group to include additional employers, trades representatives, and key stakeholders; identify leaders | Fall 2017 | Broadly representative, employer-led partnership established | Roster | Staff, Employers, Key Stakeholders
| 3e- Facilitate discussion and planning for regional sector strategy development | Winter-Spring 2018 | Establish buy-in for regional sector partnership and identified strategies | Minutes | Staff, Employers, Key Stakeholders
| 3f - Initiate implementation of identified sector strategy/ies | Spring 2018 | Sector strategies being implemented | Minutes | Staff, Employers, Key Stakeholders
| 3g - Implement strategies for moving people into pathways | By June 2018 | Possible cohort training to move people into skilled trades; may include instruction in basic applied construction skills or P2P-like projects; facilitate connections between skilled trades reps and local high schools | Number of methods used to promote skilled trades opportunities | Skilled Trades committee of the Northeast WDB with representation of Duluth WDB; Rural Coordinator
4 | Training and Education Partners Identified and Engaged | Jun-18 | Training providers see the value in developing non-traditional ways of delivering training and understand their role(s) | Faculty at local colleges engaged in program design and implementation | Career Pathways committees, boards, and staff
| 4a - Identify key contacts at local training and education facilities | By Jun-18 | Individuals and contact information is compiled | Contact list | Staff, Boards and Committees
| 4b - Connections with key contacts made; either individually or group (1 or more meetings) | By Jun-18 | Introductions are made; Basic education about WF system/education and training partners; career pathways; discussion of changing education and training needs | Minutes; Plan for moving forward | Staff, Boards and Committees
| 4c - WF system partners and training & education partners engaged and working together | By Jun-18 | Education and Training Partners engaged with WF System partners (Committee Roster, Minutes) | Committee Roster, Minutes | Staff, Boards and Committees
5 | Support Partners Identified and Engaged | Jun-18 | Existing and new partners identified through asset mapping process engaged in program design and understand their role(s) | Number of participating organizations | Career Pathways committees, boards, and staff
| 5a - Review final report from consultant | Summer 2017 | Initial understanding of assessment findings | Final Report
| 5b - Establish working group to develop recommendations for action | Fall 2017 | Group to thoroughly evaluate report to identify needed action | Roster of members; Minutes
| 5c - Formalize recommended actions | Spring 2018 | Clear recommendations for action based on mapping results | Minutes
| 5d - Implement recommended actions | Summer 2018 | Clear plan for moving forward | Minutes; Board Action
6 | Converse with Maher and Maher to learn about available resources and support | May-June 2017 | Awareness of technical assistance resources | Notes; Listing | Staff
| 6a - Review available resources with Board; Select appropriate direction | May-June 2017 | Board identification of technical assistance needs; plan for next steps | Minutes | Staff, Boards
| 6b - Implement technical assistance services | June-August 2017 | Technical Assistance services provided by Maher and Maher | Documentation of activities | Staff, Boards, Key Stakeholders

## GOAL #7
Goal #7 - Stakeholder Engagement (State Plan - Strategic Element #2)
This section outlines how the Workforce Development Boards in Region 2 will engage stakeholders, particularly populations experiencing the greatest inequities in educational and employment outcomes, in the development and implementation of local and regional strategies.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Meet/engage with identified representatives | 2017-06-01 | Understand best way to engage and learn what affected populations believe needs to happen so change can occur | Roster of population representatives; notes from conversations/meetings | Board, Leadership Team & Staff
| 1a - Host stakeholder event in partnership with Marnita's Table | 2017-02-01 | Relationship development; new connections; increased understanding of issues/challenges; ideas for moving forward | Participation list; report from Marnita's Table | Board, Staff
1b - Please reference additional actions outlined in Goal 1
| 1c - Conduct series of shared professional development trainings for staff of all WFC partners in the areas of implicit bias, micro aggressions, cultural awareness, and hiring practices. | 2017-09-17 | All program staff, supervisors and management have a greater awareness of cultural differences and similarities, communication styles and preferences, as well as a renewed understanding of how their own biases and world views can impact working relationships. | Pre- post-training/workshop evaluations | WFC Partner Management
2 | Develop system-wide coordinated strategies to engage more individuals with disabilities in employment activities | June 2018 | increased number of enrolled program/initiative participants reporting a disability; | Documentation of established processes to increase participation of individuals with disabilities in system programs and initiatives. | Board, WFC Partner Management
| 2a - Identify how WFC system can assist with preparing residential care staff to assess residents' employment potential | June 2017 | Gain understanding of changing regulations that affect community-based employment requirements of local residential/adult care facilities | A facilitated meeting with residential care and sheltered workshop facilities to determine how the workforce development system can assist with assessing residents' work skills and community-based employment potential | WFC partner management, including VRS
| 2b - Provide career planning and exploration resources to youth with disabilities | Ongoing | more youth with disabilities have post-secondary employment and/or training plans | Activity tracking akin to current Career EdVenture tracking methodology | youth program staff, including VRS transitions staff
3 | Use networks established in goal #5 to engage people in poverty and other identified target populations | through June 2018 | Opportunity to connect with non-program participants on employment needs and barriers to accessing system resources | Number of non-profit community services used for outreach; number of individual WFC-oriented focus groups conducted | Board and program staff
| 3a - Identify consultant to facilitate focus groups to discern what will enhance welcoming atmosphere and outreach opportunities of local WFCs | Sept-17 | Recommendations to improve how WFCs interact with identified populations |  | Board staff
| 3b - Develop focus group questions with consultant | Sept-17 | comprehensive strategy to identify local system improvements | Outcomes of focus groups | Board staff/WFC partner management
4 | Increase collaboration with Native American populations | 2017-12-01 | More frequent collaboration with Tribal employment and training programs and increased number of Native Americans program participants | increase of number of Native American participants in programs and initiatives; Native American participation on regional leadership/boards | Boards, board staff, program administration and staff
| 4a - Maintain presence at Fond du Lac Tribal and Community College | Ongoing | Increased participation of Native Americans in programs & initiatives; | Consistent and regular presence of counseling staff at FDLTCC | NEMOJT staff
| 4b - Connect with tribal WIOA programs to identify opportunities for alignment and leveraging funds to achieve shared goals | 2017-06-01 | Understanding of Tribal WIOA programs and identified opportunities for working closer | Identification and engagement of tribal WIOA program contacts | NEMOJT administration
| 4c - Educate staff on Native American culture | September-17 | Staff gain better understanding of factors affecting Native American education, employment, and cultural aspects that influence Native individuals; counseling staff become more culturally sensitive and creative when designing employment and training strategies for Native participants; counseling staff become aware of any implicit bias or micro aggressions that may negatively impact their interactions with Native participants | Number of training sessions; workshop evaluations; all partner staff receive training | WFC partner management
5 | Connect with groups that are already working on these issues - Take Action, Employment Table, Cross Cultural Alliance, state agencies, etc. | Ongoing | Increased collaboration and information sharing around key issues; reduced duplication of efforts | Report outs in Board Minutes and documentation of meetings | Board and staff

## GOAL #8
Goal #8 - Submission of Local Plans that Align with the Regional Plan (Regulation 679.510.2.ii)
This section documents action related to review and approval of Local and Regional Plans (Local Areas 3 and 4; Region 2) over the first 2 years of the WIOA State Combined Plan.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | LWDA 3 Submission of Local Plan | Plan submitted | Review and Approval of Local Plan by DEED | Confirmation from DEED (pending) | Michelle Ufford
2 | LWDA 4 Submission of Local Plan | Plan submitted | Review and Approval of Local Plan by DEED | Confirmation from DEED (pending) | Paula Reed
3 | Submission of Regional Plan for Region 2 | 2017-03-01 | Review and Approval of Regional Plan by DEED | Confirmation from DEED | Michelle Ufford and Paula Reed