## plan
Goal #1 - Establishing Regional Leadership Approach (Regulation 679.510 a.1.i/v)
| Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source/Evaluation Method | Person(s) Responsible | Comments
| Membership list of the oversight committee and a regional MOU submitted | Action Complete - May - 16
| Create Equity Taskforce, including community members. The Equity Taskforces compliment the great work already being done by the MaxAbility Taskforce, the Salute Southern MN Veterans Network and the Youth Taskforces of the WDB | August, 2016 | Stronger community engagement, other benefits | Roster of members
| Commitment to diversify regional/local boards through Subcommittee work | June, 2018 | Deeper communication and understanding among subcommittee members and staff | Roster of members
Goal #2- Negotiating Performance Standards (Regulation 679.510 a.1.viii)
Key Action Steps
| Designated members of the negotiating process identified; the process was included in the MOU | Action Complete - May - 16
Goal #3 - Regional Service Strategies (Regulation 679.510 a.1.ii/vi)
Key Action Steps
| SE MN Regional Luncheon on Diversity and Inclusion (coordinated outreach efforts) including a listening session for community members | 2016-08-01 | Equity Taskforces of the WDB #8 established; Sub-groups of WDB #8 to develop plan for how board can engage in relation to addressing employment disparities. Members of WDB #18 were in attendance and part of the taskforces developed from this event. | Meeting Minutes; Meetings and/or conversations with Community | Staff and Equity Taskforce Members
| Marnita's Table Employer Training/Event (coordinated outreach efforts between WDB #8 and #18) | 2017-03-01 | Identify individuals and organizations to engage; understand how they want to be engaged; understand what those affected believes needs to change to address issues; employers will have a better understanding of implicit bias and micro-aggressions in the workplace | DEED | Marnita's Table staff as contracted by DEED with assistance from Randy and Dave as needed
| Share program, training and support service policies between WDBs (support service alignment/shared program policies) | July 2017, anticipated | Consistent training and support policies between the WDBs; better understanding of separate policies; cooperative agreement statement | Consistent policies when appropriate | WDB Directors
| Utilize Best Places to Work process to evaluate and identify Best Practices within employers across our region, focusing on best equity and inclusion practices | April, 2017 and annually | Shared best practices related to equity and inclusion | Best Places to Work survey | Personnel Dynamics Consulting and WDB staff
| Utilize the Business Service Specialists and WDI Placement Specialists to provide information to employers about local training opportunities | April, 2017 and ongoing | Information provided to employers about local training opportunities focused on topics such as: inclusive hiring practices, reviewing documented job requirements and postings to accurately reflect job duties, current labor market information, the business case for hiring a diverse workforce, implicit bias awareness, generational differences, and other relevant topics. | BSS and WDB Placement staff, community partners; training opportunities shared/employers trained | BSS and WDB Placement staff
| Sector-based “speed dating” event for employers and job seekers | Fall, 2017 and ongoing | The intentional employment of diverse candidates | Evaluations following the event | WDB staff
| Voice of the Community focus groups | Fall, 2017 and ongoing | Collecting community information and sharing it with the Equity Taskforces for action item definition and follow-up | Voice of the Community feedback | WDB staff
Goal 4 - Coordination with Economic Development Services and Providers (Regulation 679.510 a.1.vii)
Key Action Steps
| Coordinated grant proposals and implementation | Ongoing | Alignment of economic development strategies with workforce development strategies, shared information and resources | Grants received | WDB and local EDA staff
| Potential shared position between WDI and Rochester Chamber focused on employer relationships and economic development throughout the region, contingent upon available funding, to serve as a model for other parts of the region | 2017-08-01 | Expanded connections with regional employers; improved relationships and partnership between the WDB and Chambers of Commerce (Economic Development) | Increased employer recognition and connection to WDBs, Successful attainment of WIOA Employer Engagement measure | WDB and local Chambers of Commerce
| Continued strategic economic development work with Aim 2 Win (the tri-state collaboration), Seven Rivers EDA and Community Economic Development Agency (CEDA) | Ongoing | Shared information among the three states/regions, increased grant opportunities | Grants received | Aim 2 Win Executive Directors
| Continued strategic economic development work with the Destination Medical Center (DMC) groups, focused on workforce shortages | Ongoing | Shared information among the groups, Career Pathway development, employer/job seeker connections | Increased career pathway development, broader awareness of WFC services | WDB staff
| Continued work with the SE MN Together project, a grantee of the Southeast Minnesota Initiative Foundation (SMIF); includes engagement from WDI AND Winona WDB staff; Community members from across SE MN, Winona EDA, CEDA and the Seven Rivers Alliance. | Ongoing | Increased partnership opportunities across the region, grant opportunities, addressing of workforce challenges (housing, childcare, transportation, etc.) across the region | Grants received | WDB staff
Goal 5 - Identify populations experiencing inequities in education and employment outcomes (State Plan Goal #1)
Key Action Steps
| Improved engagement with identified diverse community leaders and organizations to provide input, make connections, engage in process, etc. | Ongoing | Increased understanding and sharing of best practices in education and training for diverse populations; increased collaboration; avoidance, reduction or elimination of duplication of services; increased resource sharing | Increased success for diverse WDB customers; increased credential/employment measures | WDB staff
| New partnership development focused on Career Pathways in Healthcare, IT, Construction, and Public Service for specific populations in coordination with partners including CLUES, Hennepin County, Common Cause and Hispanic Contractors | Ongoing | Shared resources providing additional career pathway entrance points for targeted populations | Increased employment rates/numbers served | WDB Staff and Partner Organizations
| Marnita's Table Employer Training/Event (coordinated outreach efforts) | 2017-03-01 | Identify individuals and organizations to engage; understand how they want to be engaged; understand what those affected believes needs to change to address issues; employers will have a better understanding of implicit bias and micro-aggressions in the workplace | DEED | Marnita's Table staff as contracted by DEED with assistance from Randy and Dave as needed
| Continue the Marnita's table momentum by hosting two regional summits to engage employers and continue the discussion on inequities for both woman in non-traditional employment and formerly incarcerated individuals. Racial Equity discussions will continue through the regional work being done by the WDB's and their partners at the Diversity Council and Project FINE. Youth work will continue at the local level with the Regional Pathways Coordinator developing a calendar of events mapping the activities being coordinated and held at the high schools throughout the region. | 2017-12-31 | Bi-annual Summits held addressing workplace equity; Calendar of youth activities | Attendee lists; Resulting action items | Taskforce Subcommittee Members; WDB Staff
| Transition to Equity-Based Taskforce Subcommittee Structure of the WDB | 2016-08-01 | Focused attention on the equity issues related to the following: Women in Non-Traditional Employment, Diversity & Inclusion, MaxAbility, Salute Southern MN (Veteran's network), Youth, Previously Incarcerated | Demographics information for individuals placed in to employment/hired | Taskforce Subcommittee Members
| Ongoing work of MaxAbility and Salute Southern MN taskforce committees targeting persons with disabilities and veterans | Ongoing | Increased employment within these populations; three Veterans Networking Events and a veteran-specific job fair; five MaxAbility employer training events and a MaxAbility job fair | Increased employment rates within these populations | Taskforce Subcommittee Members
| Use of CRS, enrollment (WF1) and other data to determine base-line measures that impact targeted populations | Ongoing | Data-driven decisions, results-based accountability | WF1, CRS | WDB staff | *current demographic data attached
| Use of placement data via WF1 to determine measures that impact employers (i.e. number of employers that have hired WFC customers, total number of job seekers placed within specific employers, number of employers participating in hiring events/job fairs, etc.) Use the Targeted training (Hot Jobs) list as a common platform with employer input, data and involvement to increase the number of career pathways established. | Ongoing | Data-driven decisions, results-based accountability, career pathway development with strong employer engagement | WF1, job fair/hiring event data tracking; increased number of career pathwyas developed | WDB staff, Area employers
Goal #6 - Create one to three business led sector partnerships (Regulation 679.510a.1.iii/iv/vii)
Key Action Steps
| The following sector subcommittees are currently led by regional businesses: Healthcare (Mayo Clinic, FieldCrest Care Center, Olmsted Medical Center, Ministry Health/St. Elizabeth's, Gunderson Clinic, Spring Valley Senior Living), Service & Trades (Benike Construction, Manpower, KwikTrip, UA Local #6), Manufacturing (Viracon, Mrs. Gerry's, Domaille Engineering, Life Fitness, Alamco Wood Products, McNeilus Steel, Hormel, Jennie-O), Emerging Technologies (People's Rural Electric Company, United Prairie Bank, Henkel, Excel Energy, Mayo Clinic, IBM) | Reaffirmed in May, 2016 | Sector Subcommittees are charged with promoting business retention strategies, searching out grant funding for career pathways and special projects, studying relevant labor market information, determining targeted jobs and training programs, and promoting equity strategies across the region. The roster of sector partnership members is an additional outcome. | Current LMI (DEED), performance measures, targeted jobs and training lists/outcomes include demographics of those placed/hired, sector partnership roster | Sector Subcommittee Members
| Engage Maher & Maher to continue exploring Sector Partnerships and Business Engagement between both WDB #8 and WDB #18 | April 2017 and ongoing | Expanded business-led sector partnerships | Expanded partnerships, Employer Engagement WIOA Measure | WDB Leadership, Maher & Maher
| Create rosters of the individuals who will represent business partnerships across both WDB #8 and #18 | Dec. 2017 | Sector Partnership Roster | Completed roster | Sector Subcommittee Members
Goal #7 - Stakeholder Engagement (State Plan-Strategic Element #2)
Key Action Steps
| SE MN Regional Luncheon on Diversity and Inclusion (coordinated outreach efforts) including a listening session for community members | 2016-08-01 | Equity Taskforces of the WDB established; Sub-groups of WDB to develop plan for how board can engage in relation to addressing employment disparities. | Meeting Minutes; Meetings and/or conversations with Community | Staff and Equity Taskforce Members
| Equity Logic Training provided to WDB staff by the Diversity Council | 2016-12-01 | Better understanding of implicit bias | Training evaluations/summary report | Diversity Council staff
| Marnita's Table Employer Training/Event (coordinated outreach efforts) | 2017-03-01 | Identify individuals and organizations to engage; understand how they want to be engaged; understand what those affected believes needs to change to address issues; employers will have a better understanding of implicit bias and micro-aggressions in the workplace | DEED | Marnita's Table staff as contracted by DEED with assistance from Randy and Dave as needed
| Customer Engagement Interviews | 2017-05-01 | Direct communication with customers related to WDB services, suggestions for improvement | WDB staff interviews with customers/summary feedback | WDB Process Improvement Team members
| Create a roster of the individuals who represent targeted population organizations | Dec. 2017 | A roster of population representatives | Completed roster | Taskforce Subcommittee Members
Goal #8 - Submission of local plans that align with the Regional Plan (Regulation 679.510 2.ii) |  | Action Complete - May - 16 | Approved local and regional plans

## timeline
Regional Work Plan Timeline - Region 6 Southeast Minnesota |  |  | PLAN YEAR ONE |  |  |  | PLAN YEAR TWO
|  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
GOAL | Activity | 1-1-2016 to 06-30-2016 | 7-1-2016 to 9-30-2016 | 10-1-2016 to 12-31-2016 | 1-1-2017 to 3-31-2017 | 4-1-2017 to 6-30-2017 | 7-1-2017 to 9-30-2017 | 10-1-2017 to 12-31-2017 | 1-1-2018 to 3-31-2018 | 4-1-2018 to 06-30-2018
1 | Establishing Regional Leadership Approach
| Established Regional Oversight Committee | X
| Determine regional priorities and action plan | X
| Create Regional Memorandum of Understanding | X
| Create Equity Taskforces |  | X
| Diversity Regional Board Committees |  | X | x | x | x | x | x | x | x
2 | Negotiating Performance Standards
| Local WDB's identify who will participate in performance negotiations | X
| Create Regional Memorandum of Understanding that identifies the process of negotiating WIOA Performance levels | X
3 | Regional Service Strategies: Design
| Regional Leadership identifies three regional goals (included in MOU) | X
1. Identify critical career pathways in the region
2. Support regional K-12 schools with information and services for career planning and vocational education
3. Identify collaborative opportunities for outreach and employment support of diverse populations, including veterans, older workers, ex-offenders, women and minorities.
| Inventory the assets and gaps and suggest innovative solutions via hiring of a Regional Career Pathways Coordinator to serve the region |  | X
| Address specific youth inititives and young adult career pathways via the addition of .5 Regional Career Pathways Coordinator |  | X
| Regional Career Pathways Report created and shared with WDB's, GWDC and members of State Legislature |  |  | X
Regional Service Strategy: Action Steps
| Direct System Alignment via shared policies and practices across the Region; develop a Cooperative Agreement Statement | [5 empty] | X
| SE MN Regional Luncheon on Diversity and Inclusion (coordinated outreach efforts) |  | X
| Marnita's Table Employer Training/Event (coordinated outreach efforts) |  |  |  | X
Share program, training and support service policies between WDBs (support service alignment/shared program policies)
| Utilize Best Places to Work process to evaluate and identify Best Practices within employers across our region, focusing on best equity and inclusion practices |  |  |  |  | X |  |  |  | X
| Utilize the Business Service Specialists and WDI Placement Specialists to provide information to employers about local training opportunities |  |  |  |  | X |  | X |  | X
| Sector-based “speed dating” event for employers and job seekers | [6 empty] | X |  | X
| Voice of the Community focus groups | [6 empty] | X |  | X
4 | Coordination with Economic Development Services and Providers
| Potential shared position between WDI and Rochester Chamber focused on employer relationships and economic development throughout the region, contingent upon available funding, to serve as a model for other parts of the region | [5 empty] | X
| Next meeting with Aim 2 Win; the tri-state collaboration and Seven Rivers EDA; CEDA |  |  |  |  | X |  | X |  | X
| Continued work with DMC | X | X | X | X | X | X | X | X | X
| Continued work with SE MN Together |  | x | x | x | x | x | x | x | x
Winona EDA Work
5 | Identify Populations Experiencing Inequities in Education and Employment Outcomes
| Compile and share data on the outcomes of enrolled participants, breaking down the detail for the diverse populations served |  | X
| New partnership development focused on Career Pathways in Healthcare, IT, Construction, and Public Service for specific populations in coodination with partners including CLUES, Hennepin County, Common Cause and Hispanic Contractors; new Career Pathway training in place |  |  | X | X | X
| Marnita's Table Employer Training/Event (coordinated outreach efforts) |  |  |  | X
| Transition to Equity-Based Taskforce Subcommittee Structure of the WDB |  | X
| Three Veterans Networking Events and a veteran-specific job fair; five MaxAbility employer training events and a MaxAbility job fair |  |  |  | X | X | X | X | X | X
| Use of CRS, enrollment (WF1) and other data to determine base-line measures that impact targeted populations | X | X | X | X | X | X | X | X | X
| Use of placement data via WF1 and other data sources to determine measures that impact employers (i.e. number of employers that have hired WFC customers, total number of job seekers placed within specific employers, number of employers participating in hiring events/job fairs, etc.) | X | X | X | X | X | X | X | X | X
6 | Create Business-led Sector Partnerships
| Engage Maher & Maher to continue exploring Sector Partnerships and Business Engagement |  |  |  |  | X
| Create a roster of the individuals who will represent business partnerships | [6 empty] | X
7 | Stakeholder Engagement
| SE MN Regional Luncheon on Diversity and Inclusion (coordinated outreach efforts) including a listening session for community members |  | X
| Equity Logic Training provided to WDB staff by the Diversity Council |  |  | X
| Marnita's Table Employer Training/Event (coordinated outreach efforts) |  |  |  | X
| Customer Engagement Interviews |  |  |  |  | X
| Create a roster of the individuals who represent targeted population organizations | [6 empty] | X
8 | Submission of Local Plans that Align with the Regional Plan | X |  |  | X