## GOAL #1
Goal #1 - Establish Regional Leadership Approach (Regulation 679.510 a.1.i/v) 05/01/2017
Key Action Steps: Provide notation in work plan that documents the MOU has been completed and submitted.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Define Regional Leadership | 2016-05-01
| 1a. Board formalized R3LPB: Stearns-Benton Employment & Training Council (SBETC) and Central Minnesota Jobs & Training Services, Inc. (CMJTS) chief elected officials and workforce development boards elected to create the Region 3 Leadership & Planning Board (R3LPB) | 2016-12-01 | Initial roster is submitted. | Roster of Region 3 Leadership and Planning Board (R3LPB) members - indicated in Regional Plan | R3LPB | attachment A regional plan
2 | Approach Formalized
| 2a. R3LPB Memorandum of Understanding (MOU) between SBETC and CMJTS WDB and governing boards is developed. | 2016-01-01 | Operational agreement is submitted. | Region 3 Leadership and Planning Board (R3LPB) MOU | R3LPB | attachment CC regional plan
| 2b. MOU is signed by all elected voting members of the R3LPB. | 2016-02-01 | Documentation of R3LPB commitment to regional approach is signed. | Signed Region 3 Leadership and Planning Board (R3LPB) MOU | R3LPB
| 2c. Local Workforce Development Boards 5 and 17 approve R3LPB MOU. | Apr-16, May-16 | LWDBs 5 and 17 commitment to regional approach is documented. | Board minutes | LWDB 5 and 17
3 | Implementation of engagement strategies
| 3a. Professional development regarding diversity for leadership teams, board members, and staff. | Feb-17, Sept-17, Jan-18 | Populations experiencing inequities in education and employment are identified and multi-cultural events, marketing strategies, and recruitment are developed. | Event flyers, documentation of meetings, agendas, staff surveys | R3LPB, LWDBs 5 and 17, Titles I-IV WFC partner staff
| 3b. Identify stakeholders and diverse populations. | 2017-06-01 | Staff are aware of diverse populations' needs and can connect them to resources | Data report | R3LPB, LWDBs 5 and 17, Titles I-IV WFC partner staff
| 3c. Engage with community members and identified organizations representing targeted populations. | 2017-06-17 | A network of providers through which to engage stakeholders, conduct focus groups, and conduct program outreach to ensure greater awareness of system resources is developed. | Committee member rosters, meeting minutes, partnership rosters | R3LPB, LWDBs 5 and 17, Titles I-IV WFC partner staff
| 3d. Evaluate board and committee structure to identify gaps in representation of diverse constituencies | 2018-06-30 | Gaps identified Plan in place to increase representation on boards and committee | Board membership list (included in local plans) and committee rosters | R3LPB, LWDBs 5 and 17
4 | 3e. Engage stakeholders through sector activities. | Jul-16 through Jun-18 | Targeted populations can identifiy strengths and skills, explorie careers and set goals for employment through strategies developed by stakeholders. | Event flyers, documentation of meetings, agendas, participant surveys | R3LPB, LWDBs 5 and 17, Titles I-IV WFC partner staff
Conduct an evaluation process to ensure successful implementation and completion of the regional plan, the One-Stop delivery system, and employer engagement performance measures
| 4a. Complete a strategic analysis of the regional economy and select targeted sectors for developing career pathways. | 2016-02-01 | Demand driven sectors and occupations are selected (manufacturing, healthcare). | Data report | DEED, R3LPB | attachment G
| 4b. Expansion of work-based learning opportunities as a viable training option. | Jul-16 through Jun-18 | Employer engagement and participant options are increased. | Employer surveys, employer feedback | SBETC, CMJTS
| 4c. Regional Roundtables w/regional partners/entities to share Regional Plan | 2017-02-01 | Alignment with partners/entities is strengthened. | Meeting rosters and minutes | WFC staff, staff, partner staff

## GOAL #2
Goal #2 - Negotiating Performance Standards (Regulation 679.510 a.i.viii)
Key Action Steps: The work plan must include a time line for naming the individuals from each local workforce development board who will participate in the local negotiations. The outcome measure will be the list of names.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Local boards identify who will participate in negotiations | 2017-01-17 | Roster of members is identified. | Meeting Minutes | Jim Nimlos, Barbara Chaffee, Eric Day, Dina Wuornos, Harlan Madsen, Heidi Peper, Tammy Biery, Joan Bloemendaal-Gruett, Jim MacMahon
| a. Identify process for negotiating levels of performance | 2017-02-17 | Plan/process for negotiating is finalized | Meeting Minutes | LWDBs 5 and 17
| b. Begin negotiations for local levels of performance | 2017-02-17 | Negotiations are underway. | Meeting Minutes | Jim Nimlos, Barbara Chaffee, Eric Day, Dina Wuornos, Harlan Madsen, Heidi Peper, Tammy Biery, Joan Bloemendaal-Gruett, Jim MacMahon
| c. Identify local levels of performance | 2017-04-17 | Proposed levels are finalized. | Meeting Minutes | Jim Nimlos, Barbara Chaffee, Eric Day, Dina Wuornos, Harlan Madsen, Heidi Peper, Tammy Biery, Joan Bloemendaal-Gruett, Jim MacMahon
| d. Local levels of performance approved by local boards | 2017-06-17 | Boards approve local performance measures. | Meeting Minutes | LWDBs 5 and 17

## GOAL #3
Goal #3 - Regional Service Strategies (Regulation 679.510 a.1.ii/vi)
This section of the plan identifies regional strategies for administration, career, training or support services that Local Workforce Development Areas 5 and 17 have identified and cooperatively commit to working on over the first 2 years of the WIOA State Combined Plan. Key Action Steps: The work plan must include a timeline for identifying and articulating at least 3 strategies for career, training and/or support services that enhance outcomes for jobseekers and/or employers.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Regional Leadership Identifies and Selects 3 Goals |  | Directives for local area directors/staff | Meeting Minutes
2 | Coordinate career pathways opportunities in the manufacturing sector.
| 2a. Coordinated partnership and communication of sector events and initiatives with CMMA | 2017-03-01 | CMMA commits to lead role in Region 3 manufacturing even. | CMMA meeting minutes | Tim Zipoy, Les Engel, R3LPB
| 2b. Support Central Minnesota Manufacturers Association (CMMA) Manufacturing Summit | 2018-04-01 | Sector-led summit identifies manufacturing sector strengths, needs, outlook. | Event flyer | R3LPB
| 2c. CMMA hosts manufacturing summits in 2017 and 2018 | June 2017, June 2018 | Summits provide strategies to improve business operations, outreach, and recruitment strategies. | Event invitation and agenda | CMMA members, R3LPB
| 2d. Central Minnesota Tour of Manufacturing October event in EDR 6E | 2017-10-01 | Jobseekers learn about business and manufacturing and career pathway opportunities. | Event flyer, attendance roster, survey results | Vision 2040 Subcommittee Task Force, Willmar Public School District 347
| 2e. Expand Central Minnesota Tour of Manufacturing events for high school students in regions 7W and 7E. | 2018-05-01 | Additional high school students and adults learn about business, manufacturing, and career pathway opportunities | Event flyer | Chambers, secondary schools, colleges, community groups, manufacturing associations, economic development, DEED, ABE, SBETC, CMJTS, R3LPB
3 | Coordinate career pathways opportunities in the healthcare sector.
| 3a. the R3LPB, SBETC, and CMJTS coordinated the Healthcare Sector Summit, October 14, 2016 | 2016-10-01 | Identify regional hiring challenges for employers, begin solutions-based conversations | Event invitation and agenda | R3LPB, SBETC, and CMJTS
| 3b. A second Healthcare Summit is scheduled for April 21, 2017, to include nursing homes, residential care facilities, and ambulatory services | 2017-04-17 | Identify regional challenges and opportunities for employers | Event invitation and agenda | R3LPB, SBETC, and CMJTS
4 | Coordinate career pathways opportunities for diverse popluations experiencing inequities in education and employment.
| 4a. Submit joint RFP response for additional HECAP (Higher Education Career Advising Pilot) fudning. | 2017-07-17 | Additonal HECAP funds allow for increased number of regional initiatives that address career and training services needs of youth. | Regional RFP application response | SBETC, CMJTS, St. Cloud Public School District , Buffalo-Hanover-Montrose Public School District 877
| 4b. Host Job Fairs and Business Expos in Region 3 | quarterly Jul-16 through Jun-18 | Jobseekers have a venue to connect with targeted industry employers, educational institutions, and other stakeholders | Event flyer | SBETC, CMJTS, DEED, ABE, VRS, business partners
| 4c. Collaborative response to applicable RFPs serving targeted populations | ongoing | Implementation of regional strategies to address career, training, and support services needs of targeted populations | Regional RFP application response | WIOA Titles I-IV, colleges, secondary schools, community service providers, business, other partners as appropriate
| 4d. Participate in Central Minnesota’s Immigrant Employment Connection Group (IECG) - including several targeted employer events and career/job fairs. | Sep-16, Mar-17, Dec-17, Apr-17, Jun-17, Sep-17, Nov-17 | Educated employers overcome perceived barriers to hiring an immigrant workforce. | Event flyers and agendas | R3LPB, SBETC, CMJTS, IECG
| 4e. Hold one-stop partner meetings. | Jun-17, Jun-18 | Partners regionall goals are aligned. | Meeting minutes | WIOA Titles I-IV
| 4f. Complete Disabiility Employment Initiative (DEI) toolkit | 2017-01-18 | Toolkit provides people with disabilities resources to transition to employment, college, and careers by using a career pathways approach to training. | Roster of members, meeting minutes, completed toolkit | WFD providers - CMJTS, SBETC; ABEs – St. Croix Education District Metro East, Central MN East, Metro North, Metro West, Glacial Lakes ABE; College partners – Pine Technical and Community College, Ridgewater Community College, Anoka Ramsey Community College, Anoka Technical College; Employers – Guardian Angels, Parkview Care Center, Cashwise
| 4g. Suport Construct Tomorrow events in Region 3. | Mar-17, Oct-17 | High school students gain an increased understanding of construction union apprenticeship training centers and opportunities that exist for training and educaton in the trades | Event flyer | CMJTS - Rebecca Perrotti, SBETC - Tammy Biery
| 4h. Continue Human Centered Design implementation | 2017-06-18 | Additional WFCs and associate sites in Region 3 incoporate design principles that ensure the cutomer has a voice and that progrmming is meeting their needs and expectations. | List of WFCs that incorprate human centered designprinciples. | LWDA 5 and 17
| 4i. Draft a Fiscal Agent Agreement for the SFY16-17 Rural Career Counseling Coordinator Grant | 2017-06-16 | SBETC and CMJTS will jointly implement the RC3 grant in accordance with the terms determined by DEED | Reports | LWDA 5 and 17
| 4j. Convene career pathway seminars for adults in EDR 6E | 2017-05-17 | 100 adults in Willmar area who have no or limited post-secondary education will assess skills and understand career pathway opportunities in healthcare, manufacturing, business/retail, IT, auto mechanics, and agriculture. | Marketing materials, registrations, evaluations | Jodi Jordan, Ridgewater College Perkins Coordinator, Mike Boehme, Ridgwater College, Ann Trochill, Glacial Lakes ABE, Cathy Baumgartner, CMJTS | Seminar is funded by a Perkins mini-pathways to prosperity grant
4

## GOAL #4
Goal #4 - Coordination with Economic Development Services and Providers (Regulation 679.510 a.1.vii)
This section outlines strategies for aligning workforce development and economic development efforts with identified economic development partners across the region. Key Action Steps: The work plan must include a timeline for the identification of a new strategy to engage economic development.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Regional Roundtables w/ED entities to share Regional Plan | Jul-16 through Jun-18 | Strengthen alignment w/ED entities, specific to career pathway sectors being selected | Meeting rosters and minutes | R3LPB
2 | Develop strategies to increase coordination | Jul-16 through Jun-18 | Regularly shared communications, participation on sector committees | Copies of communications, meeting minutes | R3LPB
| 2a. Complete the Comprehensive Economic Development Strategy (CEDS) for Region 7W | 2017-12-01 | CEDS plan is completed and submitted to EDA; EDA approves plan. | Completed and approved plan | Jennifer Russell, Tricia Bigaouette
| 2b. Participate in Central Minnesota Quad Counties CEDS Steering Committee for Region 7W. | quarterly Jul-16 through Dec-17 | Steering committee continues operation until new governing structure is formed. | Committee/board member roster | Barbara Chaffee, Jennifer Russell
| 2c. Develop new governing structure that complies with EDA approved CEDS plan. | 2018-06-18 | EDA compliant governing structure is in place in EDR 7W. | Committee/board member roster | Barbara Chaffee, Jennifer Russell
| 2d. Continue collaboration with Wright County Economic Development Partnership | monthly Jul-16 through Jun-18 | Participation on WCEDP committee provides workforce development perspectives. | Meeting minutes | Tim Zipoy
| 2e. Support and particpante in GPS 45:93 | monthly Jul-16 through Jun-18 | GPS initiatives attract high-wage, technology based jobs, collaborate on business retention and expansion, recruit new businesses, encourage entrepreneurial activity and job growth in EDR 7. | Meeting minutes | Rebecca Perrotti
| 2f. Serve on Comprehensive Economic Development Strategy Committee for Region 7E | quarterly Jul-16 through Jun-18 | CEDS plan for EDR 7E provides an economic roadmap to diversify and strengthen regional economies. | Meeting minutes | Barbara Chaffee, Rebecca Perrotti
| 2g. Continue on board of EDR 6E Mid-Minnesota Development Commission | quarterly Jul-16 through Jun-18 | Board position advocates for workforce development in 6E and provides input regarding EDR 6E CEDS. | Meeting minutes | Cathy Baumgartner
| 2h. Participate in Willmar Lakes Area Vision 2040. Strategy #2 Workgroup | quarterly Jul-16 through Jun-18 | Workgroup initiatives strengthen the region’s occupational diversity through a strategic mix of workforce training, economic measurement, enhanced career options, and support for entrepreneurs. | Meeting minutes | Cathy Baumgartner
| 2i. Participate in the Greater St. Cloud Development Corporation (GSDC) | quarterly Jul-16 through Jun-18 | Opportunities to engage community leaders, foster business growth, expand and nurture the area's talent base and support the communities that make up the greater St. Cloud region are identified. | Meeting minutes | Jennifer Russell

## GOAL #5
Goal #5 - Identify the Populations Experiencing Inequities in Educational and Employment Outcomes (State Plan Goal #1)
This section outlines the basis for identifying populations most affected by educational/employment disparities and gaps in services for identified populations. Key Action Steps: The work plan, based on the identified populations, must provide a time line for outlining the specific roles and responsibilities of the communities and organizations for designing career pathways for focused populations as described in the state plan. This can be included as part of a plan for each career pathway designed, to fulfill the outcome measure.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Assess demographic data | 2017-06-17 | Understand who is impacted and idenfity gaps in services for identified populations | Data report | R3LPB and staff
| 1a. Complete Central Minnesota regional profile assessment. | 2016-10-01 | Data directs effective decision making for the establishment of regional strategies. | Data report | R3LPB, DEED Data Analyst
| 1b. Complete asset mapping of resources. | 2018-01-01 | Gaps in servicesare identified. | Asset mapping final report | Kristin Yeager
| 1c. Complete Rural Career Counselor Coordinator (RC3) high school asset mapping. | 2018-01-01 | Sector strategies needed and career pathways available are identified. | Asset mapping final reports | RC3 counselors | College is doing asset mapping of high schools
2 | Utiliize community needs assessment data | 2017-06-17 | identify areas of concern and issues that negatively impact identified populations | Community needs assessment final report | R3LPB and staff
| 2a. Administer a community needs assessment to clients, partners, businesses, education facilities, local government, community agencies | 2017-02-17 | Identified needs are reviewed and strategies to address gaps are offered. | Final report | Leslie Wojtowic, staff
3 | Identify community leaders and organizations that serve disadvantaged populations such as county jails and county services, IECG, technical colleges, CAP agencies, RISE, Functional Industries, to engage in strategies outlined in Goal 7 | Jul-16 through Jun-18 | Boards and staff know who is serving populations experiencing inequities and with whom to connect; networks of providers through which to engage stakeholders, conduct focus groups, and conduct program outreach to ensure greater awareness of system resources is established. | List of organizations and leaders identified through board and staff networks; asset mapping initiative | R3LPB, LWDBs 5 and 17, and Titles I-IV staff
| 3a. Seek input & feedback from targeted populations and engage in development of strategies to address needs. | Jan-17 to Jun-18 | Increased successful outcomes for targeted populations. | Workforce One Data and Outcome Data Report | R3LPB, LWDBs 5 and 17, and Titles I-IV staff
| 3b. Develop and implement sector-based career pathway strategies that address the unique needs and barriers of targeted populations. | 2017-12-17 | Updated Career Pathway MOU. | Career Pathway MOU | Regional Workgroup and Career Pathway Partnerships
| 3c. Continue Disability Employment Initiative (DEI) program services. | 2018-03-01 | Access to the Workforce Center System and programs for persons with disabilitiesis increased. | List of organization leaders and staff involved in DEI committee | Leslie Wojtowicz, Tera Brooks, Staff
| 3d. Implement a Disability Resource Coordinator Level 1 training for all LWDA 5 staff | 2018-03-01 | Staff have greater awareness and promote inclusiveness in the American Job Centers. | Training roster, completion results | Leslie Wojtowicz, staff
| 3e. Convene Ability Resource Fair, a reverse job fair, for individuals with disabilities, and employers | 2018-06-01 | An innovative way of introducing businesses to people with disabilities will be accomplished. | Event flyer, business representation | Leslie Wojtowicz, staff
| 3f. Continue LIFE Project and 360° Career Success workshop facilitation in county jails | Jul-16 through Jun-18 | Projects and workshops are expanded to regional counties who do not currently have these services. | Developed plans, copies of communications, meeting minutes | Dina Wuornos, CMJTS staff, ABE
| 3g. Through IECG, conduct job fairs and events that focus on hiring immigrants. | Sep-16, Nov-17 | Productive and successful hiring events are held for employers and immigrant jobseekers | Event flyer and listing of community sponsors | LWDA 5 and 17 staff
| 3h. Collaborate with Ridgewater College Multi-cultural Outreach Coordinator | quarterly Jan-17 through Jun-18 | Collaboration results in development of multi-cultural events, marketing strategies, and program recruitment that benefit multi-cultural participants. | Event flyers, meeting minutes | Dina Wuornos, CMJTS staff, ABE
| 3i. Participate in the 8th Annual Willmar Area Cinco de Mayo Family Festival | 2017-05-01 | Established network of local providers through which we can engage stakeholdersis established. | Event flyer | CMJTS Staff, Ridgewater College
| 3j. Support Willmar Area Multicultural Business Center | Jul-16 through Jun-18 | A referral network through which LWDA 5 may engage multicultural entrepreneurs is established. | Meeting minutes | Cathy Baumgartner
| 3k. Participate in Partner for Student Success (PFSS) | 2018-06-01 | Participation on PFSS committees provides PFSS with workforce development perspectives. | Meeting minutes | Tammy Biery

## GOAL #6
Goal #6 - Create 1-3 Business Led Sector Partnerships (Regulation 679.510 a.1.iii/iv/vii and State Plan - Strategic Element #1)
This section outlines the industry sectors identified for career pathways and employer-led partnerships in Region 3, including the expected outcomes to be achieved over the two-year program period for this goal. Key Action Steps: The work plan needs to identify the time line for naming the individuals who will #1: represent the business partners, #2: the specific organizations representing targeted populations, and #3: those providing specific services that create the pathway. A roster of sector partnership members can serve as the outcome measure.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Assess LMI to identify key sectors w/demand occupations |  | Scope of options for initial pathways development is narrowed. | Data report
| 1a. Access the technical assistance of Maher & Maher | 2017-04-01 | Sector strategy policy, certification standards, and unified business services are improved. | Meeting minutes | R3LPB, Maher & Maher
| 1b. Complete a strategic analysis of the regional economy and select targeted sectors for developing career pathways | 2016-02-01 | Demand driven sectors and occupations are selected | data report | DEED labor market analyst, R3LPB
| 1c. Share data report with WFC business serivces partner staff | 2017-05-17 | Business services partner staff will knowledge to meet business needs | Data report adminstered | R3LPB
2 | Establish Healthcare (demand driven) employer- led sector partnerships | 2018-06-01 | Business leaders commit to lead strategic implementation of sector efforts | Roster of participants and meeting minutes
| 2a. Convene Healthcare Sector Summits | Oct-16, Apr-17 | Two healthcare summits are held; workforce issues and opportunities are identified. | Event flyer | R3LPB
| 2b. Establish a sector-led committee from Healthcare Summit attendees | 2017-09-01 | A healthcare sector-led committee is formed. Initiatives help to increase number of qualified healthcare workers. | Committee roster, meeting minutes | R3LPB
| 2c. Convene Healthcare Alliance sector partnership meetings | quarterly Jul-16 through Jun-18 | Qualified healthcare workers increase to meet sector needs. | Meeting minutes | Pine Technical and Community College, EDR 7E partners, CMJTS
| 2d. Convene CentraCare Health led sector partnership meetings | quarterly Jul-16 through Jun-18 | Qualified healthcare workers increase to meet sector needsi n EDR 7W. | Committee roster, meeting minutes | R3LPB, CentraCare, business partners, SBETC, CMJTS, ABE
3 | MANUFACTURING (demand driven): Establish employer- led sector partnerships. |  | Business leaders commit to lead strategic implementation of sector efforts. | Roster of participants and meeting minutes
| 3a. Support Central Minnesota Manufacturers Association (CMMA) sector parnerships | monthly Jul-16 through Jun-18 | Qualified manufacturing workers increase to meet sector needs | Board roster, meeting minutes | Tim Zipoy, Brad Durfee, Les Engel, R3LPB
4 | RETAIL (demand driven): Establish employer-led sector partnerships. |  | Business leaders commit to lead strategic implementation of sector efforts. | Roster of participants and meeting minutes
| 4a. Hold Retail Advisory Board sector-led job fair | 2018-03-01 | Increase job entry and promotion in retail-related occupations | Board roster, event flyer | Leslie Wojtowicz, Rebecca Perrotti
5 | Support Partners Identified and Engaged
| 5a. Form sector partnerships between target population-serving organizations, community-based organizations, ABE and community colleges | Jun -2018 | Access to training and employment opportunities for jobseekers in targeted populations increases. | Partnership roster, meeting minutes | R3LPB, CMJTS, SBETC, community-based organizations, ABE, community colleges
| 5b. Promote work-based training opportunities that meet the needs of business. | 2018-06-01 | Sector needs are addressed through use of work-based training initiatives. | Marketing material, increased activities | SBETC, CMJTS
| 5c. Conduct regional employer survey for database development | 2018-03-01 | Database is created | Final report | R3LPB
| 5d. Participatein St Cloud Area Executive Director/CEO networking group | quarterly Jul-16 through Jun-18 | ED/CEO networking group gains workforce development perspective of local employers. | Meeting minutes | Tammy Biery
| 5e. Conduct regional business team meetings | quarterly Jul-16 through Jun-18 | Regional employer needs, training programs, upcoming events, and resources and servicessare identified, shared, and alligned. | Roster of participants, meeting minutes | LWDAs 5 and 17
| 5f. Expand the Human Resource (HR) Employer Network groups | quarterly Jul-16 through Jun-18 | Participation in HR networking group for sector partners to gain regional support for their business needs increases. | Roster of participant,meeting minutes | LWDAs 5 and 17
| 5g. Support regional CEO high school initiative. | Sep-16, Sep-17 | Additional site in Region 3 are aware of and implement a CEO program. | Media reports | LWDAs 5 and 17
| 5h. Support employer seminars in Region 3 | ongoing | An increased number of employers attend regional employment seminars. | Roster of participants. | LWDAs 5 and 17
| 5i. Update the Business Resource Directory | 2017-01-18 | Use of the tool as a resource by new and developing businesses in Region 3. | Completed document | LWDAs 5 and 17

## GOAL #7
Goal #7 - Stakeholder Engagement (State Plan - Strategic Element #2)
This section outlines how the Workforce Development Boards in Region 3 will engage stakeholders, particularly populations experiencing the greatest inequities in educational and employment outcomes, in the development and implementation of local and regional strategies. Key Action Steps: The work plan must identify the targeted populations experiencing inequities in educational and employment outcomes and demonstrate engagement through the sector activities. A roster of population representatives can serve as the outcome measure.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Professional development regarding diversity for leadership teams, board members, and staff. |  | Better understanding of implicit bias, micro aggressions, and cultural awareness |  | R3LPB, LWDBs 5 and 17, WFC staff, staff, partner staff
| 1a. Leadership attend "Understanding White Privilege" training provided by College of St. Scholastica | 2017-01-01 | Leadership has a better understanding of what white privilege is, how it is conferred and what individuals can do to promote fairness and equity. | Event flyer | CMJTS Executive Team, College of St. Scholastica staff trainers
| 1b. Host Marnita’s Table (diversity training). | 2017-02-01 | Individuals and organizations have increased skills to plan and develop strategies to engage diverse populations in workforce development. | Event flyer, ISI regional plan | Marnita's Table staff, R3LPB, LWDBs 5 and 17, staff
| 1c. Participate in staff diversity training (Implicit Bias) at Anoka Ramsey Community College | 2017-02-17 | Populations experiencing inequities in education and employment are identified; staff better understand hidden employment barries of these populations. | Event flyer | CMJTS, ARCC/ATC
| 1d. Staff attend "Understanding White Privilege" | 2017-09-01 | Staff has a better understanding of what white privilege is, how it is conferred and what individuals can do to promote fairness and equity. | Event flyer | LWDAs 5 and 17 WFC staff, College of St. Scholastica staff trainers
| 1e. Attend CLIMB Theatre Presents: Feeling History, African American Reach for Equality, CMJTS and SBETC leadership team training | 2017-02-01 | Leadership has a better understanding of America’s history of racism and how it continues to shape the experience of Black Americans | Event flyer | CMJTS, SBETC leadership staff
| 1f. Attend PANDA training delivered through ABE providers. | 2018-06-01 | Staff have a better understading of resources available for students with disabilities. | Event flyer, training agenda | ABE, Titles I-IV partner staff
| 1g. Provide career pathways training for staff serving individuals with criminal histories. | by Jun-18 | Staff have an increased knowledge of how to help ex-offenders overcome employment and retention barriers. | Event flyer, training agenda | ABE, Titles I-IV partner staff
2 | Meet/engage with identified representatives and community leaders. |  | Staff understand how to engage with and learn what multi-culural populations need to overcome employment barriers. |  | R3LPB, LWDBs 5 and 17, WFC staff, staff, partner staff
| 2a. Convene Bias Reduced Hiring training for regional employers. | by Jan-18 | Stakeholder (business) engagement and inclusiveness through the building of cross-racial competence is increased. | Training contracts with regional employers | LWDAs 5 and 17, College of St. Scholastica staff trainers, participating employers
| 2b. Particpate in quarterly meetings with Ridgewater College Multicultural Outreach Coordinator. | quarterly Jan-17 through Jun-18 | Populations experiencing inequities in education and employment are identified; multi-cultural events, marketing strategies, and recruitment to serve these populations are developed. | Rosters of participants, meeting minutes | CMJTS, SBETC, Titles I-IV partner staff, college Multicultural Outreach Coordinators
| 2c. Identify and establish relationships with all college multicultural coordinators within Region 3. | by Jun-18 | Populations experiencing inequities in education and employment are identified; multi-cultural events, marketing strategies, and recruitment to serve these populations are developed throughout Region 3. | Rosters of participants, meeting minutes | CMJTS, SBETC, Titles I-IV partner staff, college Multicultural Outreach Coordinators
3 | Develop system-wide coordinated strategies to engage more individuals with disabilities in employment activities. |  | Number of enrolled program/initiative participants reporting a disability increases.
| 3a. Create a roster of agency representatives for individuals with disabilities. | 2017-10-17 | Representatives serving persons with disabilities are identified and opportunities for greater collaboration are developed. | Rosters of participants, meeting minutes | R3LPB, LWDBs 5 and 17, WFC staff, staff, partner staff including RISE, Functional Industries, Vocational Rehab Services, Options, Inc., PANDA, PHASE
4 | Use networks established in goal #5 to engage people in poverty and other identified target populations
| 4a. Facilitate Career Trek, a 5-day, 20-hour program | monthly Jan-17 through Jun-18 | Strategies for helping targeted populatoins identify strengths and skills, explore careers and begin setting goals for their employment futureare identified. | Participant attendance count | SBETC staff
| 4b. Develop a roster of regional community action agency partner representatives. | 2017-10-01 | Programs available to serve low-income families in need opportunities for greater collaboration are identified. | Rosters of members | WFC staff, staff, partner staff TriCAP, Wright County Community Action, United Community Action Partnership, Lakes & Pines CAC
| 4c. Increase collaborative efforts between regional adult basic education providers and workforce development providers | ongoing | Collaboration and information sharing around key issues increases; integrated services to meet the educational and training needs of our communities increases. | Reports to LWDBs in minutes, documentaiton of meetings, documentaiton of collaborative efforts | WFC staff, staff, partner staff, St Cloud ABE, Glacial Lakes Adult Basic Education, Monticello ABE, Metro North ABE Elk River, SCRED, Central MN-East ABE
5 | Increase collaboration with diverse populations |  | Best practices to engage affected populations are identified and implemented. |  | R3LPB, LWDBs 5 and 17, WFC staff, staff, partner staff
| 5a. Use designated funding to provide a bilingual career planner onsite at the La Cruz Community Center. | 2017-09-17 | La Cruz Community Center remains open to facilitate work readiness programs designed to assist diverse populations. | Contract for services | SBETC staff, La Cruz Community Center
| 5b. Support IECG planned events including job fairs to engage jobseekers from diverse populations. | 2017-11-01 | Employment barriers between the diverse workforce and employers are addressed and employment increases. | Event schedule, event flyers | IECG, Titles I-IV partners, communtiy-based organizations
| 5c. Develop a working relationship with MN Extension Services Southwest Region. | 2017-06-17 | The educational needs of individuals with mental health issues or developmental disabilities are identified; collaborative efforts assist in becoming more welcoming of immigrants. | Documentation of meetings, meeting minutes | Cathy Baumgartner, Extension Services staff, regional businesses
| 5d. Establish a relationship with the African Development Center (ADC) and meet quarterly to promote engagement with the community and involvement in WFC programs | 2017-09-17 | Staff gain better understanding of factors affecting immigrant populations and education, employment, and cultural aspects that influence individuals; ADC plays an active role in planning regional initiatives. | Documentation of meetings, meeting minutes | Cathy Baumgartner, ADC staff, WFC staff
| 5e. Coordinate a referral process for use of the MCIS ABE version to assist low-skilled jobseekers. | 2017-06-01 | Low-skilled jobseekers create an employment portfolio, take career assessments, and explore job search and educational resources. | Referrals to ABE, data reports regarding use | Titles I-IV partners, ABE
| 5f. Establish a seamless referral system among Titles I-IV partners/programs. | 2018-06-01 | Program access improvements for all individuals. | Documentation of strategies, developed forms, implementation | Titles I-IV partners
| 5g. Distribute refurbished computers to Sherburne County individuals working with a CMJTS employment specialist | 2016-07-01 | Decrease the number of individuals without a computer | Distribution of computers | CMJTS
| 5h. Provide youth ages 18-24 the opportunity to work along-side master stone masons and learn industry basics | 2017-06-17 | Young adults gain hands on experience in a career pathway and transition from work experience to a college training program | Enrollment records | CMJTS, Anoka Ramsey Community College, Steger Wilderness Center
| 5i. Provide youth the opportunity to receive hands on training in the construction trades | 2017-09-16 | Young adults gain hands on training in construction and receive a level 1 certification presented by the Carpenters Union, Local 930 | Enrollment records | SBETC, St. Cloud Technical High School

## GOAL #8
Goal #8 - Submission of Local Plans that Align with the Regional Plan (Regulation 679.510.2.ii)
This section documents action related to review and approval of Local and Regional Plans (Local Areas 5 and 17; Region 3) over the first 2 years of the WIOA State Combined Plan.
# | Key Action Steps | Expected Completion Date | Expected Outcomes | Data Source & Evaluation Method | Person(s) Responsible | Comments
1 | Submit LWDA 5 Local Plan | Plan submitted | DEED reviews and Approves Local Plan. | Confirmation from DEED (pending) | Barbara Chaffee
2 | Submit LWDA 17 Local Plan | Plan submitted | DEED reviews and Approves Local Plan. |  | Tammy Biery
3 | Submit Region 3 Plan | 2017-03-31 | DEED reviews and Approves Local Plan. | Confirmation from DEED | Barbara Chaffee and Tammy Biery